## Web
TestID | Scenario | Test Title | Pre Condition | Test Type | Test Data | Test Step | Expected Result | Planned Date | Actual Result | Execution Date | Status
TC_01 | Authentication | Register with valid Data | Register Page https://qa.alta.id/auth/register | Positive | { "fullname": "Agung Pratama", "email": "agung@gmail.com20", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | Register Process PASSED | 2022-05-16 | Register Process PASSED | 2022-05-16 | Success
TC_02 | Authentication | Register with invalid Email | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama", "email": "agung20", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | Register Process FAILED | 2022-05-16 | Register Process PASSED | 2022-05-16 | Fail
TC_03 | Authentication | Register with numeric Username | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "123123", "email": "agung@gmail.com21", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert "can't use numeric data on username" - Register Process FAILED | 2022-05-16 | Register Process PASSED | 2022-05-16 | Fail
TC_04 | Authentication | Register with numeric Email | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama", "email": "123123123123", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert "can't use numeric data on email" - Register Process FAILED | 2022-05-16 | Register Process PASSED | 2022-05-16 | Fail
TC_05 | Authentication | Register with blank data | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "", "email": "", "password": "" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "unable to submit blank data" - Register Process FAILED | 2022-05-16 | Register Process FAILED | 2022-05-16 | Success
TC_06 | Authentication | Register with spaces | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": " ", "email": " ", "password": " " } | 1. Enter Test Data 2. Click Register Button | - generate alert message "unable to submit blank data" - Register Process FAILED | 2022-05-16 | Register Process FAILED | 2022-05-16 | Success
TC_07 | Authentication | Register with blank username | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "", "email": "agung@gmail.com22", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "please fill username" - Register Process FAILED | 2022-05-16 | Register Process FAILED | 2022-05-16 | Success
TC_08 | Authentication | Register with blank email | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama", "email": "", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "please fill email" - Register Process FAILED | 2022-05-16 | Register Process FAILED | 2022-05-16 | Success
TC_09 | Authentication | Register with blank password | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama", "email": "agung@gmail.com23", "password": "" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "please fill password" - Register Process FAILED | 2022-05-16 | Register Process FAILED | 2022-05-16 | Success
TC_10 | Authentication | Register with existing account | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama", "email": "agung@gmail.com", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "username and email already used by another account" - Register Process FAILED | 2022-05-16 | Register Process FAILED | 2022-05-16 | Success
TC_11 | Authentication | Login with valid Data | Login Page https://qa.alta.id/auth/login | Positive | { "email": "agung@gmail.com", "password": "agung123" } | 1. Enter Test Data 2. Click Login Button | Login Process PASSED | 2022-05-16 | Login Process PASSED | 2022-05-16 | Success
TC_12 | Authentication | Login with invalid Email | Login Page https://qa.alta.id/auth/login | Negative | { "email": "okeng@gmail.com", "password": "agung123" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-16 | Login Process FAILED | 2022-05-16 | Success
TC_13 | Authentication | Login with invalid Password | Login Page https://qa.alta.id/auth/login | Negative | { "email": "agung@gmail.com", "password": "anubro" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-16 | Login Process FAILED | 2022-05-16 | Success
TC_14 | Authentication | Login with numeric Email | Login Page https://qa.alta.id/auth/login | Negative | { "email": "123123", "password": "agung123" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-16 | Login Process PASSED | 2022-05-16 | Fail
TC_15 | Authentication | Login with blank data | Login Page https://qa.alta.id/auth/login | Negative | { "email": "", "password": "" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-16 | Login Process FAILED | 2022-05-16 | Success
TC_16 | Authentication | Login with spaces | Login Page https://qa.alta.id/auth/login | Negative | { "email": " ", "password": " " } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-16 | Login Process PASSED | 2022-05-16 | Fail
TC_18 | Authentication | Login with blank email | Login Page https://qa.alta.id/auth/login | Negative | { "email": "", "password": "agung123" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-16 | Login Process FAILED | 2022-05-16 | Success
TC_19 | Authentication | Login with blank password | Login Page https://qa.alta.id/auth/login | Negative | { "email": "agung@gmail.com", "password": "" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-16 | Login Process FAILED | 2022-05-16 | Success
TC_20 | Product | Product Category | Home Page https://qa.alta.id/ | Positive | { "kategori":"kesehatan" } | 1. Click Drop Down menu 2. Select category (test data) | - Select Category Process PASSED - Homepage show product based on category | 2022-05-16 | Homepage doesn't show any product | 2022-05-16 | Fail
TC_21 | Product | Product Category | Home Page https://qa.alta.id/ | Negative | - | 1. Enter Home Page | - Select Category Process PASSED - Homepage show product based on category | 2022-05-16 | Homepage show all product | 2022-05-16 | Success
TC_22 | Product | Product Detail | Home Page https://qa.alta.id/ | Positive | { "Tensi Darah Elektrik" } | 1. Click Detail Button on Product | - Page Directed to Tensi Darah Elektrik Product Detail Page PASSED | 2022-05-16 | - Page Directed to Tensi Darah Elektrik Product Detail Page PASSED | 2022-05-16 | Success
TC_23 | Cart | Add to cart | Home Page https://qa.alta.id/ | Positive | { "Tensi Darah Elektrik" } | 1. Click Beli Button on Product 2. Click Cart Button | - Tensi Darah Elektrik added to Cart PASSED | 2022-05-16 | - Tensi Darah Elektrik added to Cart PASSED | 2022-05-16 | Success
TC_24 | Cart | View Cart | Home Page https://qa.alta.id/ | Positive | - | 1. Click Cart Button | - Page Redirected to Cart Page PASSED | 2022-05-16 | - Page Redirected to Cart Page PASSED | 2022-05-16 | Success
TC_25 | Cart | Increase Product Quantity | Home Page https://qa.alta.id/ | Positive | { "Tensi Darah Elektrik" } | 1. Click Beli Button on Product 2. Click Cart Button 3. Click + Button 4. Click + Button | - Product Quantity Changed to 3 PASSED - Total Bayar Changed to 3 * Product Price PASSED | 2022-05-16 | - Product Quantity Changed to 3 PASSED - Total Bayar Changed to 3 * Product Price PASSED | 2022-05-16 | Success
TC_26 | Cart | Increase Product Quantity | Home Page https://qa.alta.id/ | Negative | { "Tensi Darah Elektrik" } | 1. Click Beli Button on Product 2. Click Cart Button 3. Click + Button 4. Click + Button | - Product Quantity Changed to 3 FAILED - Total Bayar Changed to 3 * Product Price FAILED | 2022-05-16 | - Product Quantity Changed to 3 PASSED - Total Bayar Changed to 3 * Product Price PASSED | 2022-05-16 | Success
TC_27 | Cart | Decrease Product Quantity | Home Page https://qa.alta.id/ | Positive | { "Tensi Darah Elektrik" } | 1. Click Beli Button on Product 2. Click Cart Button 3. Click + Button 4. Click - Button | - Product Quantity Changed to 1 PASSED - Total Bayar Changed to 1 * Product Price PASSED | 2022-05-16 | - Product Quantity Changed to 1 PASSED - Total Bayar Changed to 1 * Product Price PASSED | 2022-05-16 | Success
TC_28 | Cart | Decrease Product Quantity | Home Page https://qa.alta.id/ | Negative | { "Tensi Darah Elektrik" } | 1. Click Beli Button on Product 2. Click Cart Button 3. Click + Button 4. Click + Button | - Product Quantity Changed to 1 FAILED - Total Bayar Changed to 1 * Product Price FAILED | 2022-05-16 | - Product Quantity Changed to 1 PASSED - Total Bayar Changed to 1 * Product Price PASSED | 2022-05-16 | Success
TC_29 | Transaction | Pay | Home Page https://qa.alta.id/ | Positive | { "Tensi Darah Elektrik" } | 1. Click Beli Button on Product 2. Click Cart Button 3. Click Bayar Button | - Page Redirected to Transaction Page PASSED - New Transaction appear on Transaction Page PASSED | 2022-05-16 | - Page Redirected to Transaction Page PASSED - New Transaction appear on Transaction Page PASSED | 2022-05-16 | Success
TC_30 | Transaction | Pay | Home Page https://qa.alta.id/ | Negative | { "Tensi Darah Elektrik" } | 1. Click Beli Button on Product 2. Click Cart Button 3. Click Bayar Button | - Page Redirected to Transaction Page FAILED - New Transaction appear on Transaction Page FAILED | 2022-05-16 | - Page Redirected to Transaction Page PASSED - New Transaction appear on Transaction Page PASSED | 2022-05-16 | Success
TC_31 | Transaction | View Transaction | Home Page https://qa.alta.id/ | Positive | - | 1. Click Profile Icon 2. Click "Transaksi" Drop Down | - Page Redirected to Transaction Page PASSED | 2022-05-16 | - Page Redirected to Transaction Page PASSED | 2022-05-16 | Success
TC_32 | Transaction | View Transaction | Cart Page https://qa.alta.id/order | Negative | - | 1. Click Profile Icon 2. Click "Transaksi" Drop Down | - Page Redirected to Transaction Page FAILED | 2022-05-16 | - Page Redirected to Transaction Page PASSED | 2022-05-16 | Success

## API
TestID | Scenario | Test Title | Description | Test Type | Request Type | API Endpoint | Test Data / Request Body | Test Step | Expected Result |  | Planned Date | Actual Result | Execution Date | Status
[9 empty] | Response Code | Response Body
TC_01 | Categories | Get All Categories | Send Request with VALID endpoint | Positive | GET | https://be-qa.alta.id/api/categories | - | Send API Request to EndPoint | 200 | [ { "ID": 1, "Name": "buku", "Description": "" } ] | 2022-05-16 | Succesfully Get all categories data | 2022-05-16 | PASS
TC_02 | Categories | Get All Categories | Send Request with INVALID endpoint | Negative | GET | https://be-qa.alta.id/api/categorie | - | Send API Request to EndPoint | 404 | not found | 2022-05-16 | not found | 2022-05-16 | PASS
TC_03 | Categories | Get All Categories | Send Request with NO CONNECTION | Negative | GET | https://be-qa.alta.id/api/categories | - | Send API Request to EndPoint | 404 | not found | 2022-05-16 | not found | 2022-05-16 | PASS
TC_04 | Categories | Create Category | Send Request with VALID endpoint | Positive | POST | https://be-qa.alta.id/api/categories | { "name": "kesehatan" } | Send API Request to EndPoint | 201 | { "data": { "ID": 1001, "Name": "gadget", "Description": "" } } | 2022-05-16 |  | 2022-05-16
| Categories | Create Category | Send Request with VALID endpoint and Existing Data | Negative | POST | https://be-qa.alta.id/api/categories | { "name": "kesehatan" } | Send API Request to EndPoint | 201 | { "data": { "ID": 1001, "Name": "gadget", "Description": "" } } | 2022-05-16 |  | 2022-05-16
TC_06 | Categories | Create Category | Send Request with VALID endpoint and numeric Name | Negative | POST | https://be-qa.alta.id/api/categories | { "name": "1234" } | Send API Request to EndPoint | 201 | { "data": { "ID": 1001, "Name": "gadget", "Description": "" } } | 2022-05-16 |  | 2022-05-16
TC_08 | Categories | Create Category | Send Request with INVALID endpoint | Negative | POST | https://be-qa.alta.id/api/categorie | { "name": "kesehatan" } | Send API Request to EndPoint | 404 | not found | 2022-05-16 | not found | 2022-05-16
TC_09 | Categories | Create Category | Send Request with NO CONNECTION | Negative | POST | https://be-qa.alta.id/api/categories | { "name": "kesehatan" } | Send API Request to EndPoint | 404 | not found | 2022-05-16 | not found | 2022-05-16
TC_10 | Product | Get All Products | Send Request with VALID endpoint | Positive | GET | https://be-qa.alta.id/api/products | - | Send API Request to EndPoint | 200 | Succesfully Get all categories data | 2022-05-16 | Succesfully Get all categories data | 2022-05-16
TC_11 | Product | Get All Products | Send Request with INVALID endpoint | Negative | GET | https://be-qa.alta.id/api/product | - | Send API Request to EndPoint | 404 | not found | 2022-05-16 | not found | 2022-05-16
TC_12 | Product | Get Product By ID | Send Request with VALID endpoint | Positive | POST | https://be-qa.alta.id/api/products/100 | - | Send API Request to EndPoint | 200 |  | 2022-05-16 |  | 2022-05-16
TC_13 | Product | Get Product By ID | Send Request with INVALID endpoint | Negative | POST | https://be-qa.alta.id/api/product | - | Send API Request to EndPoint | 404 | not found | 2022-05-16 | not found | 2022-05-16
TC_14 | Product | Get Product By ID | Send Request with VALID endpoint and alphabetical ID | Negative | POST | https://be-qa.alta.id/api/products/abc | - | Send API Request to EndPoint | 400 | bad request (Invalid Data) | 2022-05-16 | { "error": "strconv.Atoi: parsing \"abc\": invalid syntax" } | 2022-05-16
TC_15 | Product | Create Product | Send Request with VALID endpoint | Positive | POST | https://be-qa.alta.id/api/products | { "name": "Vakum Cleaner", "price": 500000, "categories": [ 3, 6 ] } | Send API Request to EndPoint | 201 |  | 2022-05-16 |  | 2022-05-16
TC_16 | Product |  | Send Request with blank name | Negative | POST | https://be-qa.alta.id/api/products | { "name": "", "price": 500000, "categories": [ 3, 6 ] } | Send API Request to EndPoint | 400 |  | 2022-05-16 |  | 2022-05-16
TC_17 | Product |  | Send Request with blank price | Negative | POST | https://be-qa.alta.id/api/products | { "name": "Vakum Cleaner", "price": , "categories": [ 3, 6 ] } | Send API Request to EndPoint | 400 |  | 2022-05-16 |  | 2022-05-16
TC_18 | Product |  | Send Request with numerical name | Negative | POST | https://be-qa.alta.id/api/products | { "name": 1234, "price": 500000, "categories": [ 3, 6 ] } | Send API Request to EndPoint | 400 |  | 2022-05-16 |  | 2022-05-16
TC_19 | Product |  | Send Request with alphabetical price | Negative | POST | https://be-qa.alta.id/api/products | { "name": "Vakum Cleaner", "price": "oke", "categories": [ 3, 6 ] } | Send API Request to EndPoint | 400 |  | 2022-05-16 |  | 2022-05-16
TC_16 | Product | Create Product | Send Request with INVALID endpoint | Negative | POST | https://be-qa.alta.id/api/product | { "name": "Vakum Cleaner", "price": 500000, "categories": [ 3, 6 ] } | Send API Request to EndPoint | 404 | not found | 2022-05-16 |  | 2022-05-16
TC_17 | Authentication | Register | Send Request with valid Data | Positive | POST | https://be-qa.alta.id/api/auth/register | { "fullname": "Agung Pratama", "email": "agung@gmail.com", "password": "agung123" } | Send API Request to EndPoint | 201 | { "data": { "ID": -, "Fullname": "Agung Pratama", "Email": "agung@gmail.com", "Password": "agung123" } } | 2022-05-16 |  | 2022-05-16
TC_18 | Authentication | Register | Send Request with invalid Email | Negative | POST | https://be-qa.alta.id/api/auth/register | { "fullname": "Agung Pratama 2", "email": "agung", "password": "agung123" } | Send API Request to EndPoint | 400 | { "error": "email is required" } | 2022-05-16 |  | 2022-05-16
TC_19 | Authentication | Register | Send Request with numeric Username | Negative | POST | https://be-qa.alta.id/api/auth/register | { "fullname": "123123", "email": "agung@gmail.com", "password": "agung123" } | Send API Request to EndPoint | 400 | bad request (Invalid Data) | 2022-05-16 |  | 2022-05-16
TC_20 | Authentication | Register | Send Request with numeric Email | Negative | POST | https://be-qa.alta.id/api/auth/register | { "fullname": "Agung Pratama 3", "email": "123123", "password": "agung123" } | Send API Request to EndPoint | 400 | bad request (Invalid Data) | 2022-05-16 |  | 2022-05-16
TC_21 | Authentication | Register | Send Request with blank data | Negative | POST | https://be-qa.alta.id/api/auth/register | { "fullname": "", "email": "", "password": "" } | Send API Request to EndPoint | 400 | bad request (Invalid Data) | 2022-05-16 |  | 2022-05-16
TC_22 | Authentication | Register | Send Request with spaces | Negative | POST | https://be-qa.alta.id/api/auth/register | { "fullname": " ", "email": " ", "password": " " } | Send API Request to EndPoint | 400 | bad request (Invalid Data) | 2022-05-16 |  | 2022-05-16
TC_23 | Authentication | Register | Send Request with blank username | Negative | POST | https://be-qa.alta.id/api/auth/register | { "fullname": "", "email": "agung@gmail.com", "password": "agung123" } | Send API Request to EndPoint | 400 | { "error": "username is required" } | 2022-05-16 |  | 2022-05-16
TC_24 | Authentication | Register | Send Request with blank email | Negative | POST | https://be-qa.alta.id/api/auth/register | { "fullname": "Agung Pratama 4", "email": "", "password": "agung123" } | Send API Request to EndPoint | 400 | { "error": "email is required" } | 2022-05-16 |  | 2022-05-16
TC_25 | Authentication | Register | Send Request with blank password | Negative | POST | https://be-qa.alta.id/api/auth/register | { "fullname": "Agung Pratama 5", "email": "agung@gmail.com", "password": "" } | Send API Request to EndPoint | 400 | { "error": "password is required" } | 2022-05-16 |  | 2022-05-16
TC_26 | Authentication | Register | Send Request with existing account | Negative | POST | https://be-qa.alta.id/api/auth/register | { "fullname": "Agung Pratama", "email": "agung@gmail.com", "password": "agung123" } | Send API Request to EndPoint | 400 | { "error": "ERROR: duplicate key value violates unique constraint \"users_email_key\" (SQLSTATE 23505)" } | 2022-05-16 |  | 2022-05-16
TC_27 | Authentication | Login | Send Request with valid Data | Positive | POST | https://be-qa.alta.id/api/auth/login | { "email": "agung@gmail.com", "password": "agung123" } | Send API Request to EndPoint | 201 | { "data": { "ID": -, "Fullname": "Agung Pratama", "Email": "agung@gmail.com", "Password": "agung123" } } | 2022-05-16 |  | 2022-05-16
TC_28 | Authentication | Login | Send Request with invalid Email | Negative | POST | https://be-qa.alta.id/api/auth/login | { "email": "agung", "password": "agung123" } | Send API Request to EndPoint | 400 | { "error": "email is required" } | 2022-05-16 |  | 2022-05-16
TC_29 | Authentication | Login | Send Request with blank data | Negative | POST | https://be-qa.alta.id/api/auth/login | { "email": "", "password": "" } | Send API Request to EndPoint | 400 | bad request (Invalid Data) | 2022-05-16 |  | 2022-05-16
TC_30 | Authentication | Login | Send Request with spaces | Negative | POST | https://be-qa.alta.id/api/auth/login | { "email": " ", "password": " " } | Send API Request to EndPoint | 400 | bad request (Invalid Data) | 2022-05-16 |  | 2022-05-16
TC_31 | Authentication | Login | Send Request with blank username | Negative | POST | https://be-qa.alta.id/api/auth/login | { "email": "agung@gmail.com", "password": "agung123" } | Send API Request to EndPoint | 400 | { "error": "username is required" } | 2022-05-16 |  | 2022-05-16
TC_32 | Authentication | Login | Send Request with blank email | Negative | POST | https://be-qa.alta.id/api/auth/login | { "email": "", "password": "agung123" } | Send API Request to EndPoint | 400 | { "error": "email is required" } | 2022-05-16 |  | 2022-05-16
TC_33 | Authentication | Login | Send Request with blank password | Negative | POST | https://be-qa.alta.id/api/auth/login | { "email": "agung@gmail.com", "password": "" } | Send API Request to EndPoint | 400 | { "error": "password is required" } | 2022-05-16 |  | 2022-05-16
TC_34 | Transaction | Get All Transactions | Send Request | Positive | GET | https://be-qa.alta.id/api/orders | Authorization: Bearer [token from login response body] | Send API Request to EndPoint | 100 | { "data": [ { "Product": "Panci", "Price": 240000, "Quantity": 2, "Subtotal": 480000 } ] } | 2022-05-16 | succesfully get all transaction data | 2022-05-16
TC_35 | Transaction | Create Transaction | Send Request with valid Data | Positive | POST | https://be-qa.alta.id/api/orders | Authorization: Bearer [token from login response body] [ { "product_id": 1, "quantity": 2 } ] | Send API Request to EndPoint | 201 | { "data": [ { "ID": 2426, "User": { "ID": 5433, "Fullname": "anu", "Email": "akang", "Password": "123123123" }, "Product": null, "Quantity": 2 } ] } | 2022-05-16 |  | 2022-05-16
TC_36 | Transaction | Create Transaction | Send Request with VALID endpoint and alphabetic product_id | Negative | POST | https://be-qa.alta.id/api/categories | Authorization: Bearer [token from login response body] [ { "product_id": "aku", "quantity": 2 } ] | Send API Request to EndPoint | 201 | { "error": "json: cannot unmarshal string into Go struct field OrderCreate.product_id of type uint" } | 2022-05-16 |  | 2022-05-16
TC_37 | Transaction | Create Transaction | Send Request with VALID endpoint and alphabetic quantity | Negative | POST | https://be-qa.alta.id/api/categories | Authorization: Bearer [token from login response body] [ { "product_id": 1, "quantity": "aku" } ] | Send API Request to EndPoint | 201 | { "error": "json: cannot unmarshal string into Go struct field OrderCreate.product_id of type uint" } | 2022-05-16 |  | 2022-05-16
TC_38 | Transaction | Create Transaction | Send Request with VALID endpoint and blank product id | Negative | POST | https://be-qa.alta.id/api/categories | Authorization: Bearer [token from login response body] [ { "product_id": , "quantity": 2 } ] | Send API Request to EndPoint | 201 | { "error": "json: cannot unmarshal string into Go struct field OrderCreate.product_id of type uint" } | 2022-05-16 |  | 2022-05-16
TC_39 | Transaction | Create Transaction | Send Request with VALID endpoint and blank quantity | Negative | POST | https://be-qa.alta.id/api/categories | Authorization: Bearer [token from login response body] [ { "product_id": 1, "quantity": } ] | Send API Request to EndPoint | 201 | { "error": "json: cannot unmarshal string into Go struct field OrderCreate.product_id of type uint" } | 2022-05-16 |  | 2022-05-16
TC_40 | Ratings | Get Product Rating | Send Request with valid Data | Positive | GET | https://be-qa.alta.id/api/products/:id/ratings | "product_id": 1 | Send API Request to EndPoint | 200 | { "data": 2 } | 2022-05-16 | { "data": 2 } | 2022-05-16
TC_41 | Ratings | Get Product Rating | Send Request with VALID endpoint and alphabetic product_id | Negative | GET | https://be-qa.alta.id/api/products/:id/ratings | "product_id": 1 | Send API Request to EndPoint | 200 | { "error": "strconv.Atoi: parsing \"a\": invalid syntax" } | 2022-05-16 | { "error": "strconv.Atoi: parsing \"a\": invalid syntax" } | 2022-05-16
TC_42 | Ratings | Set Product Rating | Send Request with valid Data | Positive | POST | https://be-qa.alta.id/api/products/:id/ratings | "product_id": 1 | Send API Request to EndPoint | 201 |  | 2022-05-16 | { "data": { "ID": 2003, "Name": "Vakum Cleaner", "Description": "", "Price": 500000, "Ratings": 4, "Categories": [ { "ID": 3, "Name": "alat", "Description": "" }, { "ID": 6, "Name": "kesehatan", "Description": "" } ] } } | 2022-05-16
TC_43 | Ratings | Set Product Rating | Send Request with VALID endpoint and alphabetic product_id | Negative | POST | https://be-qa.alta.id/api/products/:id/ratings | "product_id": 1 | Send API Request to EndPoint | 201 |  | 2022-05-16 | { "error": "strconv.Atoi: parsing \"abc\": invalid syntax" } | 2022-05-16
TC_44 | Comments | Get Product Comments | Send Request with valid Data | Positive | GET | https://be-qa.alta.id/api/products/:id/comments | "product_id": 1, { "content": "mantap nih" } | Send API Request to EndPoint | 200 | { "data": { "ID": 1, "Content": "mantap nih" } } | 2022-05-16 | { "data": [ { "ID": 1005, "Content": "mantap nih", "User": null, "Product": null, "Comment": null } ] } | 2022-05-16
TC_45 | Comments | Get Product Comments | Send Request with VALID endpoint and alphabetic product_id | Negative | GET | https://be-qa.alta.id/api/products/:id/comments | "product_id": 1, { "content": "mantap nih" } | Send API Request to EndPoint | 200 | { "error": "strconv.Atoi: parsing \"abc\": invalid syntax" } | 2022-05-16 | { "error": "strconv.Atoi: parsing \"abc\": invalid syntax" } | 2022-05-16
TC_46 | Comments | Post a Product Comment | Send Request with valid Data | Positive | POST | https://be-qa.alta.id/api/products/:id/comments | "product_id": 1, { "content": "mantap nih" } | Send API Request to EndPoint | 201 | { "data": { "ID": 1, "Content": "mantap nih" } } | 2022-05-16 |  | 2022-05-16
TC_47 | Comments | Post a Product Comment | Send Request with VALID endpoint and alphabetic product_id | Negative | POST | https://be-qa.alta.id/api/products/:id/comments | "product_id": 1, { "content": "mantap nih" } | Send API Request to EndPoint | 201 | { "error": "strconv.Atoi: parsing \"abc\": invalid syntax" } | 2022-05-16 | { "error": "strconv.Atoi: parsing \"abc\": invalid syntax" } | 2022-05-16

## Mobile
TestID | Scenario | Test Title | Pre Condition | Test Type | Test Data | Test Step | Expected Result | Planned Date | Actual Result | Execution Date | Status
TC_01 | Authentication | Register with valid Data | Register Page https://qa.alta.id/auth/register | Positive | { "fullname": "Agung Pratama", "email": "agung@gmail.com", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | Register Process PASSED | 2022-05-17 | Register Process PASSED | 2022-05-17 | PASS
TC_02 | Authentication | Register with invalid Email | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama 2", "email": "agung", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | Register Process FAILED | 2022-05-17 | Register Process FAILED | 2022-05-17 | PASS
TC_03 | Authentication | Register with numeric Username | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "123123", "email": "agung@gmail.com", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert "can't use numeric data on username" - Register Process FAILED | 2022-05-17 | - Register Process FAILED - Alert not generated | 2022-05-17 | PASS
TC_04 | Authentication | Register with numeric Email | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama 3", "email": "123123", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert "can't use numeric data on email" - Register Process FAILED | 2022-05-17 | - Register Process FAILED - Alert not generated | 2022-05-17 | PASS
TC_05 | Authentication | Register with blank data | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "", "email": "", "password": "" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "unable to submit blank data" - Register Process FAILED | 2022-05-17 | - Register Process FAILED - Alert generated ("data can not be empty") | 2022-05-17 | PASS
TC_06 | Authentication | Register with spaces | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": " ", "email": " ", "password": " " } | 1. Enter Test Data 2. Click Register Button | - generate alert message "unable to submit blank data" - Register Process FAILED | 2022-05-17 | - Register Process FAILED - Alert not generated | 2022-05-17 | PASS
TC_07 | Authentication | Register with blank username | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "", "email": "agung@gmail.com", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "please fill username" - Register Process FAILED | 2022-05-17 | Register Process PASSED | 2022-05-17 | FAIL
TC_08 | Authentication | Register with blank email | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama 4", "email": "", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "please fill email" - Register Process FAILED | 2022-05-17 | - Register Process FAILED - Alert generated ("data can not be empty") | 2022-05-17
TC_09 | Authentication | Register with blank password | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama 5", "email": "agung@gmail.com", "password": "" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "please fill password" - Register Process FAILED | 2022-05-17 | - Register Process FAILED - Alert generated ("data can not be empty") | 2022-05-17
TC_10 | Authentication | Register with existing account | Register Page https://qa.alta.id/auth/register | Negative | { "fullname": "Agung Pratama", "email": "agung@gmail.com", "password": "agung123" } | 1. Enter Test Data 2. Click Register Button | - generate alert message "username and email already used by another account" - Register Process FAILED | 2022-05-17 | - Register Process FAILED - Alert generated ("gagal") | 2022-05-17
TC_11 | Authentication | Login with valid Data | Login Page https://qa.alta.id/auth/login | Positive | { "email": "agung@gmail.com", "password": "agung123" } | 1. Enter Test Data 2. Click Login Button | Login Process PASSED | 2022-05-17 |  | 2022-05-17
TC_12 | Authentication | Login with invalid Email | Login Page https://qa.alta.id/auth/login | Negative | { "email": "okeng@gmail.com", "password": "agung123" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-17 |  | 2022-05-17
TC_13 | Authentication | Login with invalid Password | Login Page https://qa.alta.id/auth/login | Negative | { "email": "agung@gmail.com", "password": "anubro" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-17 |  | 2022-05-17
TC_14 | Authentication | Login with numeric Email | Login Page https://qa.alta.id/auth/login | Negative | { "email": "123123", "password": "agung123" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-17 |  | 2022-05-17
TC_15 | Authentication | Login with blank data | Login Page https://qa.alta.id/auth/login | Negative | { "email": "", "password": "" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-17 |  | 2022-05-17
TC_16 | Authentication | Login with spaces | Login Page https://qa.alta.id/auth/login | Negative | { "email": " ", "password": " " } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-17 |  | 2022-05-17
TC_17 | Authentication | Login with blank email | Login Page https://qa.alta.id/auth/login | Negative | { "email": "", "password": "agung123" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-17 |  | 2022-05-17
TC_18 | Authentication | Login with blank email | Login Page https://qa.alta.id/auth/login | Negative | { "email": "agung@gmail.com", "password": "" } | 1. Enter Test Data 2. Click Login Button | - Login Process FAILED - generate alert message "invalid email or password" | 2022-05-17 |  | 2022-05-17

## RoleMatrix
MODULE | FEATURE | DESKRIPSI | User | System / API
Auth | Register | Register New User | v | v
| Login | User gain access to enter web system | v | v
| Logout | User end access from system | v
Product | Product Category | User view some products from a category | v
| Product Detail | User view a product detail | v
| Add to cart | User add item to cart | v
| Add Product Rating | User give rating to a product |  | v
| Get All Categories | Get all categories data |  | v
| Create Category | Create a category |  | v
| Get All Products | Get all products data |  | v
| Get Product By ID | Get a product data |  | v
| Create Product | Create a product |  | v
| Get Product Rating | Get a product rating data |  | v
| Set Product Rating | Set a product rating data |  | v
| Get Product Comments | Get a product comments |  | v
| Post a Product Comment | Post a product comment |  | v
Cart | View Cart | User view items added to cart | v
| Increase Product Quantity | User increase product quantity | v
| Decrease Product Quantity | User derease product quantity | v
| Pay | User pay items | v
Transaction | View Transaction | User view processed transactions | v
| Get All Transactions | Get All Transactions Data |  | v
| Create Transaction | Create a Transaction Data |  | v